## Project Plan
Project Title
Start Date
End Date
Project Lead(s) | Name | Role | Contact Information
External Stakeholders | Name | Relationship | Contact Information
Describe external organizations and entities your project is accountable to
Project Justification The need that the project is addressing
Project Description A brief overview of the project in plain language!
Project Objectives The key objectives including but not limited to the schedule, budget and project criteria
Project Deliverables A summary of the key project deliverables which would indicate the successful completion of the project
Project Requirements/Acceptance
Exclusions What are some items that you are NOT delivering on? What's outside the scope of work?
Limitations The key constraints acting on this project, impacting timeline, budget and project quality
Risk Management What could go wrong? How likely is each risk? How will you prevent them? | Risk | Likelihood | Impact
|  | (Low, Med, High) | (Low, Med, High)
|  | (Low, Med, High) | (Low, Med, High)
Assumptions A list of assumptions that affects the conduct and operation of the project
High-Level Project Schedule | Task Description | Ideal Due Date | Person Responsible
Budget Summary
Agreement Who needs to sign off on this project? Have they?
Overview
A project scope of work document summarizes high level information so that everyone is aligned on key project elements. Because of it's concise nature, this document can be shared with team members and stakeholders to provide a quick overview of a larger project. Some of sections of a project scope document will have detailed supporting documents.
Tips and Tricks·
- Having discussions and debates to iron out and define the listed project elements before you start - will help guide decision making and ensure alignment throughout the project.
- Make sure this document is easilty accessible to your team and others
Note on A37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These two would be included should you choose to call this a “project plan”. A project plan needs to include three key aspects: scope, timeline and budget. BUT, if we call this a project scope statement, then we don’t need to include it. This might be helpful since there are other sections for budget and timeline, but none for scope defintion.

## Work Breakdown Structure
WBS Number | Task Title | Description | Responsible | Accountable | Consulted | Informed | Dates Active | Start Date | Due Date | Status
1 | Project Conception and Initiation
1.1 | Project Charter
1.1.1 | Project Charter Revisions
1.2 | Research
1.3 | Projections
1.4 | Stakeholders
1.5 | Guidelines
1.6 | Project Initiation
2 | Project Definition and Planning
2.1 | Scope and Goal Setting
2.2 | Budget
2.3 | Communication Plan
2.4 | Risk Management
3 | Project Launch and Execution
3.1 | Status and Tracking
3.2 | KPIs
3.2.1 | Monitoring
3.2.2 | Forecasts
3.3 | Project Updates
3.3.1 | Chart Updates
4 | Project Performance / Monitoring
4.1 | Project Objectives
4.2 | Quality Deliverables
4.3 | Effort and Cost Tracking
4.4 | Project Performance
Overview
This excel page integrates two key project management tools: a workbreakdown structure and a RACI matrix.
What is a Work Breakdown Structure?
A project work breakdown plan will help you think about what needs to be accomplished to complete a project. It containts all of the details and tasks you need to complete, organized in a hierarchical levels.
Most projects have multiple components. These are typically organized under different work packages - groups of related tasks that form more manageable "sub-projects". As the planning progresses, you will need to be aware of many moving parts and smaller details. Having the deadlines and related tasks in one will not only help you complete tasks in a timely way, but will also help you figure out where the team needs support.
(TIP: Create a decision tree to help you visualize your project's work breakdown structure. )
RACI Matrix
Responsible: People or stakeholders who do the work. They must complete the task or objective or make the decision. Several people can be jointly Responsible.
Accountable: Person or stakeholder who is the "owner" of the work. He or she must sign off or approve when the task, objective or decision is complete. This person must make sure that responsibilities are assigned in the matrix for all related activities. Success requires that there is only one person Accountable.
Consulted: People or stakeholders who need to give input before the work can be done and signed-off on. These people are "in the loop" and active participants.
Informed: People or stakeholders who need to be kept "in the picture." They need updates on progress or decisions, but they do not need to be formally consulted, nor do they contribute directly to the task or decision.
with the event planning team to review this document and adjust it accordingly.
Tips and Tricks·
- Schedule regular check-ins with your team to review this document and adjust it accordingly
- Add notes to the work plan as you progress, so that you can keep track of key conversations or pieces of information.

## Communications Matrix
Communications Type | Goal Why do we have this communication type? | Channel | Frequency How often? | Audience Who is it for? | Responsible Who is the lead? | Contributors Who helps to draft this? | Deliverables What are the supporting documents
Project Team Meetings |  | Face to face or Zoom
Overview
Project Communication Matrix summarizes how you will be communicating important information throughout a project. Information flow and the exchange of ideas and information is key to successful projects.

## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Company Name | [5 empty] | How to use template: https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead | Project Start: |  | 2024-04-26
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2024-04-22 to 2024-06-16
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2024-04-22 to 2024-06-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 Title
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Task 1 | Name | 50% | 2024-04-26 | 2024-04-29 | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Task 2 |  | 60% | 2024-04-29 | 2024-05-01 | 3
| Task 3 |  | 50% | 2024-05-01 | 2024-05-05 | 5
| Task 4 |  | 25% | 2024-05-05 | 2024-05-10 | 6
| Task 5 |  |  | 2024-04-30 | 2024-05-02 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2 Title
| Task 1 |  | 50% | 2024-05-01 | 2024-05-05 | 5
| Task 2 |  | 50% | 2024-05-03 | 2024-05-08 | 6
| Task 3 |  |  | 2024-05-08 | 2024-05-11 | 4
| Task 4 |  |  | 2024-05-08 | 2024-05-10 | 3
| Task 5 |  |  | 2024-05-08 | 2024-05-11 | 4
Sample phase title block | Phase 3 Title
| Task 1 |  |  | 2024-05-11 | 2024-05-16 | 6
| Task 2 |  |  | 2024-05-17 | 2024-05-21 | 5
| Task 3 |  |  | 2024-05-22 | 2024-05-27 | 6
| Task 4 |  |  | 2024-05-28 | 2024-06-01 | 5
| Task 5 |  |  | 2024-05-22 | 2024-05-26 | 5
Sample phase title block | Phase 4 Title
| Task 1 |  |  | date | date | #VALUE!
| Task 2 |  |  | date | date | #VALUE!
| Task 3 |  |  | date | date | #VALUE!
| Task 4 |  |  | date | date | #VALUE!
| Task 5 |  |  | date | date | #VALUE!
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Overview
A event breakdown plan will help you think about all of the details and tasks you need to complete leading up to the event.
As the planning progresses and the event nears, you will need to be aware of may moving parts and smaller details. Having the deadlines and related tasks in one will not only help you complete tasks in a timely way, but will also help you figure out where the team needs support.
What is a Work Package?
- Visualize your project work breakdown by creating a decision tree
RACI Matrix
Responsible: People or stakeholders who do the work. They must complete the task or objective or make the decision. Several people can be jointly Responsible.
Accountable: Person or stakeholder who is the "owner" of the work. He or she must sign off or approve when the task, objective or decision is complete. This person must make sure that responsibilities are assigned in the matrix for all related activities. Success requires that there is only one person Accountable.
Consulted: People or stakeholders who need to give input before the work can be done and signed-off on. These people are "in the loop" and active participants.
Informed: People or stakeholders who need to be kept "in the picture." They need updates on progress or decisions, but they do not need to be formally consulted, nor do they contribute directly to the task or decision.
with the event planning team to review this document and adjust it accordingly.
Create a Project Schedule
- Upload the work breakdown schedule into an online software, like Google Sheets, Trello, Monday.com or Asana for an dynamic way to view and interact with you and your team to communicate and keep each other in the loop. https://docs.google.com/spreadsheets/d/10Lop5gquDYcQNHSIw-12coKVe3dK98eWBiwkHqvSknI/edit#gid=0 -
Tips and Tricks·
- Schedule regular check-ins with your team to review this document and adjust it accordingly
- Add notes to the work plan as you progress, so that you can keep track of key conversations or pieces of information.

## Budget
Sources of Revenue
Item | Previous Year Sources | Current Year Expected | Current Year Actuals | Projections & Recommendations For Next Year | Breakdown of Items
Total | 0 | 0 | 0
Logistics
Item | Previous Year Sources | Current Year Expected | Current Year Actuals | Projections & Recommendations For Next Year | Breakdown of Items
Total | 0 | 0 | 0
OTHER/ALL
Item | Previous Year Sources | Current Year Expected | Current Year Actuals |  | Breakdown of Items
Total | 0 | 0 | 0
Overall Total | 0 | 0 | 0