## Overview
Other Tabs in this Workbook | Applicable? | Summary | Amount
Event Proposal | Yes/No |  | 0
Budget | Yes/No | Actuals to date | 0
Invitees and RSVPS | Yes/No | Actuals to date
Communications Plan | Yes/No
Event Program | Yes/No
Event Breakdown | Yes/No
Run of Show | Yes/No
Volunteers | Yes/No
Materials Checklist | Yes/No
Appreciation and Thank you | Yes/No
Assessment/Metrics | Yes/No
Event Summary and Recommendations | Yes/No
Overview
This resource is meant to help you plan an event, from beginning to end. You can adjust the sheets to best fit your event, and you do not have to use every single tab.
How to use this workbook
Each sheet contains a template for you to fill out. In the same sheet, there is a grey text box similar to this one containing important information such as:
- Overview of the sheet
- Tips and tricks
- Helpful checklists
- Additional information

## Event Proposal
This is not something you need to hand in. Feel free to adjust this toolkit to fit your event's needs. If you need guidance or want to walkthrough the event in more detail, the APSC PD team is happy to help you!
Title of Event
Organizers
Vision
Purpose of Event
Goals of Event
How will you know this event is successful?
Has this event been organized before?
What are the key messages attendees need to know?
Event Design
Who is this event open to? Is it free or paid?
Is it an open house? panel? Online, in-person or hybrid?
What are some possible venues?
Strategic Alignment
How does this event support the goals of your student group?
Which goals does it directly support?
Logistics
Date(s):
Time(s):
Location(s):
Collaboration(s):
Attendees
Reason:
Who is invited?
Expected Number:
Risk Management/Contingency Planning
Contingency planning is an important aspect to planning any large event with multiple stakeholders. This has been proven to be even more crucial in recent years, with in-person events transitioning to virtual platforms, supply issues and last-minute changes in human resources. Developing a contingency plan early means that should there be a disruption in original plans, you have a well thought out back up plan available. Have you discussed your back up plan with your whole event planning team? Is everyone on board? Who in your event planning committee will decide when to switch to the contingency plan? Is everyone clear on who does what?
What could go wrong? How likely is each risk? How will you prevent them or what is your backup? | Risk | Likelihood | Impact | Mitigation
|  | (Low, Med, High) | (Low, Med, High)
|  | (Low, Med, High) | (Low, Med, High)
Overview
Before you delve right into planning your event, take a few minutes to think about the purpose and goals of the event. Complete the worksheet on the right to help you layout the event effectively.
Review UBC's Event policies: https://students.ubc.ca/campus-life/organizing-campus-events
Tips and Tricks
- See if others have organized similar events, and reach out to them for advice and lessons learned.
- Check in with the APSC PD team if you need help with finding a venue that fits your budget and event type.
- Book the venue as early as possible, as many (on-campus) spaces book up quickly.
Checklist
□ What other events are taking place in Engineering and on campus at the same time, or close to this event?
□ Is this event near an upcoming holiday? If so, this may impact attendance, as some people may extend their time off. or
Incorporating EDI into your event:
- Check out the UBC's Equity and Inclusion Office's website: https://equity.ubc.ca/resources/accessible-and-inclusive-event-planning/
- What are the optics in selecting this venue? Is it an inclusive space?

## Budget
Sources of Revenue
Item | Previous Year Sources | Current Year Expected | Current Year Actuals | Projections & Recommendations For Next Year | Breakdown of Items
Funds
Ticket Sales
Sponsorship
Gifts in Kind
Total | 0 | 0 | 0
Logistics
Item | Previous Year Sources | Current Year Expected | Current Year Actuals | Projections & Recommendations For Next Year | Breakdown of Items
Venue
Buildings Operations
Rentals
A/V Equipment
Catering
Security
Total | 0 | 0 | 0
OTHER/ALL
Item | Previous Year Sources | Current Year Expected | Current Year Actuals |  | Breakdown of Items
Gifts
Volunteer Appreciation
Promotional Items
Supplies (pens, name tags, etc.)
Photographer
Other **
Total | 0 | 0 | 0
Overall Total | 0 | 0 | 0
Overview
Create a budget that includes all expenses. Think about if your goal fo the event is to break even, ot raise funds.
If you have sponsors or gifts-in-kind, please let APSC PD know. If you have questions about sponsorships, we're also happy to help.
A quick note about catering:
- Catering costs add up quickly. Think about what type of catering is needed, and where you can save costs. Try to get an accurate headcount as early as possible, as this will help you to mitigate costs.
Tips and Tricks
- Reach out to the APSC PD team if you need help with anticipating event costs. We can also help you to develop a list of vendors.
- See if you have anything from previous events that you can use to help save costs

## Invitees and RSVPs
Invitees | Email | Organization/Group | RSVP | Personal Pronouns | Dietary Restrictions | Accessibility Requests | Notes
Overview
Track your RSVPs so that you are able to plan your venue, catering and event accordingly. Having all of your invite lists in a centralized place will also help you send out any key communications to them if you need to.
Tips and Tricks
- Personal outreach is a strong way to attract additional attendees.Think about how to leverage your networks.
- Think about how you are going to invite any special guests, speakers, etc.
- Try to track how invitees heard about the event, so that you have an idea of how well each different promotion/marketing channel is doing
- Ensure your RSVP question about catering requirements so that your catering accommodates all dietary restrictions and requirements

## Communications
Communications Materials | Target Group | Requirements | Timeline | Blurb | Link to communication material (and attachments)
Event Participants
Registration confirmation | Confirmed Guests
Key information/welcome package before the event | Confirmed Guests
Thank you/feedback survey | Confirmed Guests |  | Post event
See volunteer sheet for information on what to include | Volunteers
Include speaking notes/information | Speakers/Guests
Event package (vendor info, contact info, run of show, etc.) | Event organizers
Marketing to potential invitees
Internal - Students
E-newsletter (e-neus, graduate newsletter) | Current Students | https://ubcengineers.ca/eneus | Three weeks before event. Request running on a weekly basis.
Facebook groups | Current Students | Add it to the E-nEUS request.
Internal - for any
Posters - washrooms | Faculty, Studetns, Staff | communications@apsc.ubc.ca | Two weeks before event
Digital signage | Engineering Building Faculty and Students | communications@apsc.ubc.ca | Two weeks before event
Campus Partners
Canvas Page for First Year Engineering
Leverage networks of: Alumni; Co-op | Industry and Alumni
Co-op Newsletter
Online
APSC PD Website | All UBC APSC Community
Student group website
Applied Science Social Media
Twitter/X | UBC, APSC faculty, external audiences
Facebook | Current and prospective students | Tag "UBC Engineering" and we will reshare
Instagram | Current and prospective students | Tag "UBC Engineering" and we will reshare
LinkedIn | External community | Tag "UBC Engineering" and we will reshare
UBC
UBC Events | UBC community
UBC Media Relations | Media and Greater Vancouver
UBC Digital Signage | UBC campus | https://digitalsignage.ubc.ca/submission/
Ubyssey - student newspaper | All UBC Students
Overview
Ensure your marketing materials are consistent by preparing them well in advance and outlining key messaging.
Think about:
- Who is your potential invitee and is the content relevant to them?
- Is the message different depending on who your invitee is (ex. students vs industry)
- What are the key messages you would like to convey to attendees?
For marketing materials, see "Online Community and Marketing" resource.
Tips and Tricks
- Don't message too frequently, as this may have the opposite effect
- Remind guests about the event a few days out by sending them a welcome email/package.
- Include key information like maps, sign in information, and an itineraray

## Event Program
Time | Event Schedule | Goals for this part of the event… what is the purpose of this part of the event?
43559.375
9:30
43559.4167
10:30
43559.4583
11:30
43559.5
12:30
43559.5417
13:30
43559.5833
14:30
43559.625
15:30
43559.6667
16:30
43559.7083
17:30
43559.75
18:30
43559.7917
19:30
43559.8333
20:30
Overview
This is something that would be shared with your attendees. It is a high level information about the day.
Tips and Tricks
- Think about the goals for each different part of the event, this will help you with design and planning.
Incorporating EDI into your event:
- Prepare a Land Acknowledgment in advance, and include it your opening. (more info: https://students.ubc.ca/ubclife/what-land-acknowledgement). Feel free to reach out to APSC PD if you have any questions.

## Event Breakdown
Work Package | Description | Responsible | Consulted | Informed | Dates Active | Start Date | Due Date | Status
Assessment
Catering
Catering
Communications
Logistics
Materials
Visioning
Volunteering
Special Guests
Overview
A event breakdown plan will help you think about all of the details and tasks you need to complete leading up to the event.
As the planning progresses and the event nears, you will need to be aware of may moving parts and smaller details. Having the deadlines and related tasks in one will not only help you complete tasks in a timely way, but will also help you figure out where the team needs support.
*If your event has an Emcee, speakers, or panel, the APSC PD team can guide you on how to create speakers notes, etc.*
RACI Matrix
Responsible: People or stakeholders who do the work. They must complete the task or objective or make the decision. Several people can be jointly Responsible.
Accountable: Person or stakeholder who is the "owner" of the work. He or she must sign off or approve when the task, objective or decision is complete. This person must make sure that responsibilities are assigned in the matrix for all related activities. Success requires that there is only one person Accountable.
Consulted: People or stakeholders who need to give input before the work can be done and signed-off on. These people are "in the loop" and active participants.
Informed: People or stakeholders who need to be kept "in the picture." They need updates on progress or decisions, but they do not need to be formally consulted, nor do they contribute directly to the task or decision.
with the event planning team to review this document and adjust it accordingly.
Tips and Tricks
- Upload the work breakdown schedule into an online software, like Asana for an dynamic way to view and interact with you and your team to communicate and keep each other in the loop.
- Schedule regular check-ins with the event planning team to review this document and adjust it accordingly
- Know where key documents and communications from vendors, volunteers and presenters are being stored.
- Add notes to the work plan as you progress, so that you can keep track of key conversations or pieces of information.
- Add a task before the event to reconfirm siginificant parts a week before the event (catering, venue, speakers, etc.)

## Run of Show - Organizing Team
| Event Program | Detailed schedule | Volunteer Schedule | Organizer's Name | Organizer's Name | Organizer's Name
Time | Copy and paste from event program tab | Include vendor information (venue set up, take-down, catering, etc.) | This is helpful to include, so that you have a bird's eye view of what they are doing! | What is person #1 doing throughout the day? | What is person #2 doing throughout the day? | What is person #3 doing throughout the day?
43559.375
9:30
43559.4167
10:30
43559.4583
11:30
43559.5
12:30
43559.5417
13:30
43559.5833
14:30
43559.625
15:30
43559.6667
16:30
43559.7083
17:30
43559.75
18:30
43559.7917
19:30
43559.8333
43559.875
Overview
- The purpose of a run of show is to layout the timing of the different core pieces of the event in a sequential way. It shows how all of the pieces fit together for the major pieces of an event (guests, venue, event schedule, and major event organizers/leads). Run of shows may have details at the minute-by-minute level to make sure all critical details are included, including pre and post event details.
Tips and Tricks
- Think about anything you need to collect before the event, and make sure you incorporate that time into the event schedule
-- Have the key event team (and volunteers, if possible) do a walkthrough to make sure everything is as planned before the event goes live.
- Find a way to communicate with volunteers, guests and event organizers on the day. Ensure there is a phone number guests can call if they run into issues, and that there is a messaging group set up in case volunveers and event planners need to sort out any final details.
- If you find yourself running behind schedule, adjust the schedule. Some guests may have commitments and will have to leave at the end time.

## Volunteers
About the Event
Insert Event Name
Event Description
Link to the schedule for them to see
Key Contact information (during the event)
What happens if they suddenly can't make it?
Overview
Dress code:
Check in instructions:
Tip: schedule a time that is well before the event starts!
What are some FAQs they may need to know?
Catering
Registration?
Parking
Schedule
Volunteer Shift 1
Time of shift (start and end)
Volunteer Manager:
Names of Volunteers
What are their tasks? | What do they need to know to make it a smooth experience for your attendees?
(List out volunteer tasks in as much detail as you can - you want the volunteer coordinator to be able to answer most questions, rather than asking the event coordinators)
Overview
The size and format of your event will determine the number of volunteers you need. Think about bringing some additional volunteers on board in the days leading up to the event, and for the event itself.
Tips and Tricks
- Communicate with the volunteers leading up to the event - it's important for them to feel and know they are a bit part of it. The more information and details you can give them in advance, the better.
- Consider coming up with a one-pager with all of the volunteer roles and descriptions, and a one-pager with some FAQs you expect the guests to ask. (You can even give them this sheet!)
- List out volunteer tasks in as much detail as you can - you want the volunteer coordinator to be able to answer most questions, rather than asking the event coordinators.
- Try to assign roles based on the volunteer's strengths and interests
- Don't forget about food for the volunteers - it is a nice way to show appreciation for the time and work :)

## Materials Checklist
Item | Got it to bring there? | Packed it to bring back?
Printouts
Name tags
Land Acknowledgement
Event Package - Run of Show, Schedules, Volunteer documents
Vendor confirmations (venue, catering)
Technology
USB with presentations
Catering
Banquet event order and contact information
AV
Microphone etc.
Miscellaneous
Did you order coat racks, etc.?
Overview
Brainstorming this list ahead of time is key so that you have enough time to create and print anything required before the event.
Tips and Tricks
- Have on hand a list of confirmations and receipts in case any of the vendors have questions the days of. Organize them in a folder beforehand so that they are ready to go!
- Print out any key documents, like the event schedule, and run of show. If you have speakers, make sure you have a copy of their speaking notes or powerpoints.
- Thinking of making name tags? Using this list, we recommend you complete a mail merge. Google "mail merge".
Incorporating EDI into your event
- Add personal prounouns to the name tags (more info: https://equity.ubc.ca/resources/gender-diversity/pronouns/)

## Appreciation and Thank you
Role | Name | Card/Note | Other gifts (if applicable) | Cost (if applicable) | Notes
Volunteer
Facilitator
Sponsor
Special Guest
Support role
Overview
Take a moment to appreciate those who helped make the event successful.
A simple thank you card with a thoughtful message is an easy to recognize others' efforts.
If you're sending it post-event, think about including a link to the photo gallery. Include a note about how they contibute to the success of this event, and/or some postive comments you heard from guests.
Tips and Tricks
- Have extra cards, just in case you have any last minute volunteers
- One person doesn't have to write up all the cards - this is a great activity to do in a group (or assign to individuals)

## Assessment & Recommendations
External Feedback
Add survey questions here if you are planning to send a survey to attendees.
Alignment with Goals
Review your purpose and goals set out in the event proposal form.
Did your event meet these? Why or why not?
Internal Feedback
Review your event logistics and results.
Did your venue work? Is there somewhere better to hold a similar event in future?
If this event was done in collaboration with another organization, how did that work out?
Would you approach the same organization for future collaboration?
What are your other takeaways from this event?
What was the actual number of attendees?
Were there any external factors to the increased or poor turnout?
I.e. there was another major campus event at the same time, it was raining etc.
Was there adequate advertisement for the event? If applicable, how could it be improved?
Recommendations for Future Events
If you had to start the planning process over, is there anything you would do differently?
Anything you wish you’d known? Any resources you needed access to?
Tips and Tricks
Host a debrief session soon after your event to discuss key successes and learning opportunities for future events. Ensure you have a wide representation of different people who were involved, including volunteers.
https://www.extension.iastate.edu/Documents/ANR/LikertScaleExamplesforSurveys.pdf